## Sheet1
Risk | Criticality | Short Description | Mitigation Plan | Comments | Problem Ticket | Assignee
Fargate instance is not shutting down automatically | HIGH | Fargate instance is not getting shut down within proper time which is creating problem in task execution and keeping the task pending for long hours | Team manually checks the open long running fargate instance and manually close them. Terminate the existing task and relaunch it | It has a direct impact on the existing tasks, | PRB0139854 | Jagan
Tomcat server shutting down abruptly | HIGH | Tomcat servers in SailPoint is getting shutdown automatically, even sometime it becomes irresponsive due to which all the existing running tasks are getting affected | Team manually checks the server health and ensure the host is active or not. If inactive, then restart the servers. | It has a direct impact on the existing tasks, | PRB0139858 | Jagan
attribute sync discrepancy (rehire, newhire, terminated) | HIGH | Identity attributes are not in sync between Source and target applications. Discrepancy found for new hired, rehired and terminated users | Team is working on daily discrepancy fix activity which resolve the overall disparity between WD to IIQ and IIQ to Target | 1. Automation of manual discrepancy is on the way 2. Working on Custom Workday connector too | PRB0139859 | Supriyo
Manager not able to see the new hired user's password | HIGH | Temporary password for new hired users is not getting retrieved by their immediate manager | With the enhancement of Password Portal Phase 2.0, this issue will be resolved | new hired user will not be able to login to the system unless the password is reset to the permanent one. It's direct impact on their productivity | PRB0139865 | Viplav
OIG servers are going into stuck state | MEDIUM | OIG servers are getting stuck intermittently and staying stuck until the rolling restart is done | Team is doing the rolling restart to all the OIG servers in every Monday and Wednesday as part of scheduled Change Request. | Applications which are directly related to Oracle Identity Governance especially Password Portal will be impacted, Will take more than usual time to load which affects user's password rotation in time | PRB0139866 | Supriyo
Steward group conversion to MailGroup in AD | MEDIUM | All the approval steward groups available and maintained in AD are getting converted into the mailbox. Access requests in SailPoint is impacted due to this transformation. |  | Access request in SailPoint is getting affected due to this convertion. During provisioning workflow, SailPoint verifies the availability of the steward group in AD as well as the count of members in the steward group. Being the steward group as mailer group is actually creating the issue and forcing the request to get rejected automatically. | PRB0139867 | Siva
Future Work Force connection issue | MEDIUM | SailPoint -> Ping -> FWF connection is impacted |  |  | PRB0139868 | Siva
population of display name value in AD | MEDIUM | AD script is still taking care of updating the display name by removing -CW for India hired users | Long term solution already applied and it is running. Will talk to Scott to pause this script temporarily. If worked, then will officially suspend the task | Display name is broadly integrated for lots of applications in their authentication/authorization.
SailPoint and OIG Database performance issue | LOW | It is noticed rarely that both SP and OIG DB performance directly got affected due to the problem in respective task servers. Any read/write operation in DB is impacted | Team manually checks the server health and ensure the host is active or not. If inactive, then restart the servers. | Mostly it happens due to infrastructure issue mentioned in PRB0139854 and PRB0139858 | PRB0139869
downstream application is not accepting 12 character password | LOW | Unlike Password Portal, downstream applications of SailPoint are not accepting the password length of 12 characters. | With the enhancement of Password Portal Phase 2.0, this issue will be resolved | if any application is identified, AD team need to create a fine grained password policy like STAR applicaton and assigned the user to the fine grained policy group to continue with the old policy. | PRB0140050 | Supriyo
Except Merch Vendor, there is no trusted source for organization data for other vendor types | LOW | Organization data aggregation happens from MDM for Merch vendors. Rest of the org creation happens via manual SNOW intakes. If there is any data error from requestor, that could lead to issues. | Manual intervention is required to correct the data. | If any users onboarded under the wrong organization, needs to be disabled and new onboarding has to be happened. | PRB0140170 | Supriyo

## Sheet2
Key Business Metrics | FY25 | Comments
Terminated Users Validation | Total 312 Users Terminated in System | Termination happened smoothly for those users without any impact | Points | Count
| Total 308 Users terminated in Downstream application via Delta Aggregation and identity Refresh |  | Total SOP
| Total 8 Users Terminated by triggering manual Leaver Event as part of Discrepancy Fix |  | Newly Created during Holiday
New Hire Users Validation | Total 576 Users New hired and rehired users in System | Onboarding happened for newly hired users in all system without any impact. Successful password generation and interception in all other system happened properly for all users | Recently Updated during Holiday
All Users were Active in Lenel/OUD/IIQ/AD
Total 17 users were disabled in OIG which we fixed by triggering manual Rehire event
Daily Discrepancy Fix | Total 413 users found discrepant who were available in IIQ but in Workday | By running Delta Aggregation, we fixed those users
| Total 3 users found discrepant who were available in Workday but not in IIQ | By running Delta Aggregation, we fixed those users
| Total 2 users found discrepant who were Active in IIQ but disabled in AD | By running Rehire event, we fixed those users
| Total 327 users found discrepant who were Disabled in IIQ but Active in AD | By running Leaver event, we fixed those users
| Total 21 users found discrepant who were Active in IIQ but disabled in OIG | By running Mover event, we fixed those users
| Total 441 users found discrepant who were Disabled in IIQ but Active in OIG | By running Leaver event, we fixed those users
| Total 5 found discrepant where users Active in IIQ but disabled in OUD | By running Mover event, we fixed those users
| Total 200 users found discrepant who were disabled in IIQ but Active in OUD | By running Leaver event, we fixed those users
| Total 25 found discrepant where users Active in IIQ but disabled in Lenel | By running Mover event, we fixed those users
| Total 255 users found discrepant who were disabled in IIQ but Active in Lenel | By running Leaver event, we fixed those users